## Sheet1
Defect ID | Defect Reporting Date | Project Name | Project Version | Module/Submodule Name | Type of Defect | Phase in which defect is identified | Summary of Defect | Description of Defect | Severity | Priority | Status | Reported By | Reported to
DF01 | 2021-10-01 | Blood Bank Today | bbt1.0 | My Donation Report >> Add Donation Report | Wrong | System | My Donation Report accepts invalid values | 1. Visit Blood Bank Today website | Medium |  | New | Radhika Bailurkar | Rajani Sankpal
2. Login into account
3. Click on My Donation Report on Dashboard
4. Fill the report with invalid data
Expected result: Error Msg " Please fill valid credentials "
Actual result : Donation Report is added
DF02 | 2021-10-01 | Blood Bank Today | bbt1.0 | Register | Wrong | System | Register Module accepts invalid values | 1. Visit Blood Bank Today website | High |  | New | Radhika Bailurkar | Rajani Sankpal
2. Enter Full Name: 123456789
3. Enter Email ID: 123#example.com
4. Enter Mobile No.: qwertyuiop
5. Enter Password: esile395f3
6. Enter Weight: tsnno
7. Enter Pin/Zip: efgn38f0
8. Enter City/ Village: 348ge
9. Uncheck the terms & conditions
Expected Result: System throws error " Please enter valid details "
Actual Result: User is redirected to Confirm OTP page.
DF03 | 2021-10-01 | Blood Bank Today | bbt1.0 | Login | Missing | System | Sign in with Facebook not working | 1. Visit Blood Bank Today website | Medium |  | New | Radhika Bailurkar | Rajani Sankpal
2. Click on Login Button on Homepage
3. Click on Sign in with Facebook to login
Expected result : User is logged into account
Actual result : Link does not work
DF04 | 2021-10-01 | Blood Bank Today | bbt1.0 | My Messages >> Send Message | Wrong | System | Send Messages sends msgs with few fields and add it to Messages List | 1. Visit Blood Bank Today Website | High |  | New | Radhika Bailurkar | Rajani Sankpal
2. Login into Dashboard
3. Select Message for as Inquiry
4. select priority type as early
5. Click on send button
Expected Result: System throws error "Please fill all fields"
Actual Result: "Data added successfully"
DF05 | 2021-10-01 | Blood Bank Today | bbt1.0 | Navbar on Homepage | Missing | System | Video Module not working | 1. Visit Blood Bank Today website | Medium |  | New | Radhika Bailurkar | Rajani Sankpal
2. Click on Video in Navbar
Expected result : Videos are displayed
Actual result : Link does not work/Missing link